## Registration
Test Title | Test cases for Taka app | Test Case Start Date | 30.08.2023
Environment | IOS, Android | Test Case End Date | 08.09.2023
Test Case Reviewed by
|  | Test Case Developed by | Nigah Hossain
TC ID | Areas of the Feature | Pre-Conditions | Test Items | Test Data | Step Action | Expected Result | Note/Comments
TC_01 | Registration | The navigation page has been working | Verify that, the navigation page has a working Login/Registration button |  | 1. Open the app 2. Click on the Login/Registration button | Clicking on the button should take to the next page
TC_02 |  | The navigation page has been working | Verify that, the registration page asks to scan NID card's front page |  | 1. Open the app 2. Click on the Login/Registration button 3. Keep the NID card in front of camera | This should open camera
TC_03 |  | The navigation page has been working | Verify that, the registration page asks to scan NID card's back page |  | 1. Open the app 2. Click on the Login/Registration button 3. Keep the NID card's back page in front of camera | This should ask to capture back page
TC_04 |  | The navigation page has been working | Verify that, the registration page asks to take the user's raw picture |  | 1. Open the app 2. Click on the Login/Registration button 3. Complete NID scanning 4. Take own picture | This should open camera
TC_05 |  | The navigation page has been working | Verify that, a unique 5 digits PIN needs to be set up by calling *247# |  | 1. Open phone's dial option 2. Call *247# 3. Choose “Activate Mobile Menu” 4. Enter a 5 digit PIN 5. Re-enter the PIN to confirm | The account should be created
TC_06 |  | The navigation page has been working | Verify that, the registration page has phone number option |  | 1. Open the app 2. Click on the Login/Registration button 3. Complete NID and picture scanning 4. Input numbers | Phone number field should be taking phone number
TC_07 |  | The navigation page has been working | Verify that, the phone number field allows exact 11 digits | 1782890358 | 1. Open the app 2. Click on the Login/Registration button 3. Complete NID and picture scanning 4. Input more than 11 digits | This should not allow to enter any digit after 11 digits
TC_08 |  | The navigation page has been working | Verify that, the registration page has all the phone operators available |  | 1. Open the app 2. Click on the Login/Registration button 3. Complete NID and picture scanning 4. Input number 5. Select one operator | All the sim operators options should be available
TC_09 |  | The navigation page has been working | Verify that, the registration page allows only one phone operator to be selected at a time |  | 1. Open the app 2. Click on the Login/Registration button 3. Complete NID and picture scanning 4. Input number 5. Try to select more than one operator | One operator can be selectable at a time
TC_10 |  | The navigation page has been working | Verify that, the spellings are correct |  | 1. Open the app 2. Click on the Login/Registration button 3. Complete NID and picture scanning 4. Input number 5. Check all the fields' spellings | All the spellings should be correcr

## Cash In
Test Title | Test cases for Taka app | Test Case Start Date | 30.08.2023
Environment | IOS, Android | Test Case End Date | 08.09.2023
Test Case Reviewed by
|  | Test Case Developed by | Nigah Hossain
TC ID | Areas of the Feature | Pre-Conditions | Test Items | Test Data | Step Action | Expected Result | Note/Comments
TC_01 | Cash In | The user is already registered | Verify that, the field is accepting only 11 digits number | 1782890358 | 1. Go to the "Cash In" module. 2. Input more than 11 digits | The field should accept only 11 digits
TC_02 |  | The user is already registered | Verify that inputting more than 11 digits, 'Next' option does not appear | 17828903584 | 1. Go to the "Cash In" module. 2. Input more than 11 digits 3. Try to click on the Next option | The field should should show a pop up with an error message if more than 11 digits are inputted
TC_03 |  | The user is already registered | Verify that the cash in amount is within 6 digits | 567389 | 1. Go to the 'Çash in' module 2. Input more than 6 digits | The field should should not take any digit over 6
TC_04 |  | The user is already registered | Verify that, the fields are labelled properly |  | 1. Go to the 'Cash in' module 2. Check all the fields' labels | All fields should show proper labels while hovering over
TC_05 |  | The user is already registered | Verify that, while selecting numbers or names, the whole saved list is appearing |  | 1. Go to the 'Cash in' module 2. Write number or name 3. See if the whole saved list is appearing | All the saved contacts list should be showing up
TC_06 |  | The user is already registered | Verify that, the cash in feature/button is working |  | 1. Click on the 'Cash in' module 2. Check whether it is taking to the next page | The button should be clickable
TC_07 |  | The user is already registered | Verify that, while sending money, greater amount selected than the usable balance doesn't allow the user to go forward |  | 1. Go to the 'Cash in' module 2. Select the number 3. Write an amount that is greater than the usable balance 4. See if the next button is working | It should pop up an error message
TC_08 |  | The user is already registered | If the beneficiary is not saved to the account, try to transfer the amount by manually putting the number & verify if any error message is displayed. |  | 1. Go to the 'Cash in' module 2. Write the number 3. See if it is appearing from the saved list 4. If the number isn't saved, write it manually | This should not show anything in the list if the beneficiary is not saved
TC_09 |  | The user is already registered | Verify that, if beneficiary's number is partially entered, whether total details are automatically populated on the page. |  | 1. Go to the 'Cash in' module 2. Write few digits of the number 3. See if it is appearing from the saved list | Inputting numbers should show the saved list
TC_10 |  | The user is already registered | Verify that, successful transfer message is popped up when the balance is sent. |  | 1. Go to the 'Cash in' module 2. Write the number 3. Go to next page 4.Put down the amount 5. Complete sending 6. See if any notification of successful transfer is appearing | The user should receive a confirmation message

## Cashout
Test Title | Test cases for Taka app | Test Case Start Date | 30.08.2023
Environment | IOS, Android | Test Case End Date | 08.09.2023
Test Case Reviewed by
|  | Test Case Developed by | Nigah Hossain
TC ID | Areas of the Feature | Pre-Conditions | Test Items | Test Data | Step Action | Expected Result | Note/Comments
TC_01 | Cashout | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that the 'Agent' field is taking only 11 digits | 1782890358 | 1. Go to the 'Cashout' module 2. Input more than 11 digits 3. Try to click on the Next option | It should not allow entering any digit after 11 digits
TC_02 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that inputting more than 11 digits, 'Next' option does not appear | 17828903585 | 1. Go to the 'Cashout' module 2. Input more than 11 digits 3. See if the Next option is clickable | Next option should disappear if any extra digit is entered
TC_03 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that cash out amount can be within 6 digits | 546789 | 1. Go to the 'Cashout' module 2. Choose or input agent number 3. Input the amount more than 6 digits | The 7th digit should not be taken
TC_04 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that 'Agent' field shows only saved or recently transactioned agents' list |  | 1. Go to the 'Cashout' module 2. Choose 'Agent' field 3. See if the saved agents list is showing | There should appear a list of saved agents numbers below
TC_05 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that the favorite agent number is saved for less cashout charge |  | 1. Go to the 'Cashout' module 2. Click on the 'হাজারে ১৪.৯০ টাকায় ক্যাশআউট করতে চাপুন' 3. Find the saved agent number | The number should be appearing there
TC_06 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that more agent numbers can be added |  | 1. Go to the 'Cashout' module 2. Click on the 'হাজারে ১৪.৯০ টাকায় ক্যাশআউট করতে চাপুন' 3. Click on the '+' sign at the bottom right corner | After adding the number, an error message should be popped up that only one agent number can be saved within one month
TC_07 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that QR code scanner opens to take QR code picture |  | 1. Go to the 'Cashout' module 2. Go to the QR code scan button | This should open the camera for scanning
TC_08 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that number or name field is labelled properly |  | 1. Go to the 'Cashout' module 2. Check whether the number or name field is labelled | This should show the labelling always
TC_09 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that 'ATM' field shows only instructions and list of partner banks |  | 1. Go to the 'Cashout' module 2. Go to the ATM tab 3. See the instructions tabs | There should be two seperate buttons with instructions

## Send money
Test Title | Test cases for Taka app | Test Case Start Date | 30.08.2023
Environment | IOS, Android | Test Case End Date | 08.09.2023
Test Case Reviewed by
|  | Test Case Developed by | Nigah Hossain
TC ID | Areas of the Feature | Pre-Conditions | Test Items | Test Data | Step Action | Expected Result | Note/Comments
TC_01 | Send money | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that the usable balance is showing accurate |  | 1. Go to the 'Send Money' module 2. Select the number 3. Go to the next page where usable balance is displayed | There should be displayed the accurate usable balance
TC_02 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that the favorite number is available for sending money free of cost |  | 1. Go to the 'Send Money' module 2. Check the star marked numbers in the list | The favorite number should be saved and marked as star
TC_03 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that the 'Áuto pay' option is selectable |  | 1. Go to the 'Send Money' module 2. Click on the 'Auto pay' | Áuto pay' should be a seperate option
TC_04 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that an example video is available to show how to perform auto pay option |  | 1. Go to the 'Send Money' module 2. Click on the 'Auto pay' 3. Click on the video manual | There should be a video available to show steps of enabling auto pay

## Mobile recharge
Test Title | Test cases for Taka app | Test Case Start Date | 30.08.2023
Environment | IOS, Android | Test Case End Date | 08.09.2023
Test Case Reviewed by
|  | Test Case Developed by | Nigah Hossain
TC ID | Areas of the Feature | Pre-Conditions | Test Items | Test Data | Step Action | Expected Result | Note/Comments
TC_01 | Mobile Recharge | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that, the Mobile Recharge button working |  | 1. Go to the 'Mobile recharge' 2. See whether it is moving to the next page | This should lead to the next page
TC_02 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that the 'Name or Number' field is taking only 11 digits | 1782890358 | 1. Go to the 'Mobile recharge' 2. Try to write down more than 11 digits | This should disable the Next button
TC_03 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that important notes are available for every offer | 17828903587 | 1. Go to the 'Mobile recharge' 2. Select number 3. See My offer, minutes etc tabs to see important notes | This should display in every tab except Amount
TC_04 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that the 'Name or Number' field shows all the list of saved numbers |  | 1. Go to the 'Mobile recharge' 2. See the list appearing below | This should show the list of saved numbers
TC_05 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that after entering or selecting number the next page shows all the offers |  | 1. Go to the 'Mobile recharge' 2. Select the number 3. See the next page with different tabs | There should appear different offers like Internet, My offer, Minutes etc
TC_06 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that the usable balance is showing accurately |  | 1. Go to the 'Mobile recharge' 2. Select the number 3. See the usable balance below in the next page | This should display the amount of usable balance
TC_07 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that every tab different available offers |  | 1. Go to the 'Mobile recharge' 2. Select the number 3. See the next page with different tabs | There should appear different offers like Internet, My offer, Minutes, Call rate, Bundle
TC_08 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that any offer is selectable regardless of necessary balance |  | 1. Go to the 'Mobile recharge' 2. Select the number 3. See the next page with different tabs 4. Select any offer | This should lead to the next page
TC_09 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that an "Auto recharge" option is available |  | 1. Go to the 'Mobile recharge' 2. Select the number 3. See the next page with different tabs 4. From the 'Amount' tab, see the 'Auto recharge' option | Auto recharge with settings' option should appear
TC_10 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that selecting any offer with greater amount than usable balance shows an error message before inputting pins |  | 1. Go to the 'Mobile recharge' 2. Select the number 3. Select an offer that needs more amount than the usable balance 4. Go to next 5. Input the pin 6. See the message next | This should occur an error message

## Paybill
Test Title | Test cases for Taka app | Test Case Start Date | 30.08.2023
Environment | IOS, Android | Test Case End Date | 08.09.2023
Test Case Reviewed by
|  | Test Case Developed by | Nigah Hossain
TC ID | Areas of the Feature | Pre-Conditions | Test Items | Test Data | Step Action | Expected Result | Note/Comments
TC_01 | Paybill | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that only accurate format of Credit card number allows to go further |  | 1. Go to the 'Pay bill' module 2. Choose Credit card from the list 3. Choose the bank 4. Give any number in the Card number | Entering wrong format of number should not appear the Next button
TC_02 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that entering on each type of bill opens up all the institutions of that bill paying |  | 1. Go to the 'Pay bill' module 2. Choose the company name from the list 3. See the list below | There should appear the whole list of institutions/companies
TC_03 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that any bill paid through Bkash is recorded in the 'Pay bill details' section |  | 1. Go to the 'Pay bill' module 2. Go to the 'Pay bill details' | Any bill paid through Bkash should be recorded in the 'Pay bill details' section
TC_04 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that in case of Electricity bill; after inputting the identification number, bill amount is not displayed |  | 1. Go to the 'Pay bill' module 2. Choose the company name from the list 3. Choose the bill type 4. Input the account number and contact number 5. Input the bill amount | There should not show any amount but should input the amount manually
TC_05 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that in case of water bill; the timeline is selectable for paying the bill of any specific month |  | 1. Go to the 'Pay bill' module 2. Choose the company name from the list 3. Choose the bill type 4. Select the timeline from dropdown | There should be a dropdown available in order to select timeline
TC_06 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that in case of water bill; entering more than 25 digits for bill number does not allow to go further |  | 1. Go to the 'Pay bill' module 2. Choose the company name from the list 3. Choose the bill type 4. Input more than 25 digits for the bill number | This should not appear the next button
TC_07 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that bill receipts are accurately recorded in the 'Receipt and Token' section |  | 1. Go to the 'Pay bill' module 2. Go to the 'Receipt and Token' section 3. Check Bill receipt | All the paid bill receipts should be recorded in the 'Bill receipt' section

## Test Execution
Test Title | Test cases for Taka app | Test Case Execution Start Date | 30.08.2023
Environment | IOS, Android | Test Case Execution End Date | 08.09.2023
Test Case Execution Reviewed by
|  | Test Case Execution Developed by | Nigah Hossain
TC ID | Areas of the Feature | Pre-Conditions | Test Items | Test Data | Step Action | Expected Result | Actual Result | Status |  | Priority | Note/Comments
[8 empty] | IOS | Android
TC_01 | Registration | The navigation page has been working | Verify that, the navigation page has a working Login/Registration button |  | 1. Open the app 2. Click on the Login/Registration button | Clicking on the button should take to the next page | The next page opens | Passed | Passed | High
TC_02 |  | The navigation page has been working | Verify that, the registration page asks to scan NID card's front page |  | 1. Open the app 2. Click on the Login/Registration button 3. Keep the NID card in front of camera | This should open camera | Camera opens | Passed |  | High
TC_03 |  | The navigation page has been working | Verify that, the registration page asks to scan NID card's back page |  | 1. Open the app 2. Click on the Login/Registration button 3. Keep the NID card's back page in front of camera | This should ask to capture back page | Camera opens | Passed | Passed | High
TC_04 |  | The navigation page has been working | Verify that, the registration page asks to take the user's raw picture |  | 1. Open the app 2. Click on the Login/Registration button 3. Complete NID scanning 4. Take own picture | This should open camera | Camera opens | Passed | Passed | High
TC_05 |  | The navigation page has been working | Verify that, a unique 5 digits PIN needs to be set up by calling *247# |  | 1. Open phone's dial option 2. Call *247# 3. Choose “Activate Mobile Menu” 4. Enter a 5 digit PIN 5. Re-enter the PIN to confirm | The account should be created | Account is created | Passed | Passed | High
TC_06 |  | The navigation page has been working | Verify that, the registration page has phone number option |  | 1. Open the app 2. Click on the Login/Registration button 3. Complete NID and picture scanning 4. Input numbers | Phone number field should be taking phone number | Successful | Passed | Passed | High
TC_07 |  | The navigation page has been working | Verify that, the phone number field allows exact 11 digits | 1782890358 | 1. Open the app 2. Click on the Login/Registration button 3. Complete NID and picture scanning 4. Input more than 11 digits | This should not allow to enter any digit after 11 digits | Doesn't allow | Passed | Passed | High
TC_08 |  | The navigation page has been working | Verify that, the registration page has all the phone operators available |  | 1. Open the app 2. Click on the Login/Registration button 3. Complete NID and picture scanning 4. Input number 5. Select one operator | All the sim operators options should be available | Available | Passed | Passed | High
TC_09 |  | The navigation page has been working | Verify that, the registration page allows only one phone operator to be selected at a time |  | 1. Open the app 2. Click on the Login/Registration button 3. Complete NID and picture scanning 4. Input number 5. Try to select more than one operator | One operator can be selectable at a time | Successful | Passed | Passed | High
TC_10 |  | The navigation page has been working | Verify that, the spellings are correct |  | 1. Open the app 2. Click on the Login/Registration button 3. Complete NID and picture scanning 4. Input number 5. Check all the fields' spellings | All the spellings should be correct | All the spellings are correct | Passed | Passed | High
TC_11 | Cash In | The user is already registered | Verify that, the field is accepting only 11 digits number | 1782890358 | 1. Go to the "Cash In" module. 2. Input more than 11 digits | The field should accept only 11 digits | Successful | Passed | Passed | High
TC_12 |  | The user is already registered | Verify that inputting more than 11 digits, 'Next' option does not appear | 17828903584 | 1. Go to the "Cash In" module. 2. Input more than 11 digits 3. Try to click on the Next option | The field should should show a pop up with an error message if more than 11 digits are inputted | There is a pop up | Passed | Passed | High
TC_13 |  | The user is already registered | Verify that the cash in amount is within 6 digits | 567389 | 1. Go to the 'Çash in' module 2. Input more than 6 digits | The field should should not take any digit over 6 | Successful | Passed | Passed | Medium
TC_14 |  | The user is already registered | Verify that, the fields are labelled properly |  | 1. Go to the 'Cash in' module 2. Check all the fields' labels | All fields should show proper labels while hovering over | All labels are there | Passed | Passed | Low
TC_15 |  | The user is already registered | Verify that, while selecting numbers or names, the whole saved list is appearing |  | 1. Go to the 'Cash in' module 2. Write number or name 3. See if the whole saved list is appearing | All the saved contacts list should be showing up | Successful | Passed | Passed | High
TC_16 |  | The user is already registered | Verify that, the cash in feature/button is working |  | 1. Click on the 'Cash in' module 2. Check whether it is taking to the next page | The button should be clickable | The button is clickable | Passed | Passed | High
TC_17 |  | The user is already registered | Verify that, while sending money, greater amount selected than the usable balance doesn't allow the user to go forward |  | 1. Go to the 'Cash in' module 2. Select the number 3. Write an amount that is greater than the usable balance 4. See if the next button is working | It should pop up an error message | There is a pop up | Passed | Passed | High
TC_18 |  | The user is already registered | If the beneficiary is not saved to the account, try to transfer the amount by manually putting the number & verify if any error message is displayed. |  | 1. Go to the 'Cash in' module 2. Write the number 3. See if it is appearing from the saved list 4. If the number isn't saved, write it manually | This should not show anything in the list if the beneficiary is not saved | There is nothing when no beneficiary is saved | Passed | Passed | Low
TC_19 |  | The user is already registered | Verify that, if beneficiary's number is partially entered, whether total details are automatically populated on the page. |  | 1. Go to the 'Cash in' module 2. Write few digits of the number 3. See if it is appearing from the saved list | Inputting numbers should show the saved list | There comes a list | Passed | Passed | Low
TC_20 |  | The user is already registered | Verify that, successful transfer message is popped up when the balance is sent. |  | 1. Go to the 'Cash in' module 2. Write the number 3. Go to next page 4.Put down the amount 5. Complete sending 6. See if any notification of successful transfer is appearing | The user should receive a confirmation message | The confirmation message is received | Passed | Passed | Medium
TC_21 | Cashout | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that the 'Agent' field is taking only 11 digits | 1782890358 | 1. Go to the 'Cashout' module 2. Input more than 11 digits 3. Try to click on the Next option | It should not allow entering any digit after 11 digits | Doesn't allow | Passed | Passed | High
TC_22 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that inputting more than 11 digits, 'Next' option does not appear | 17828903585 | 1. Go to the 'Cashout' module 2. Input more than 11 digits 3. See if the Next option is clickable | Next option should disappear if any extra digit is entered | Successful | Passed | Passed | High
TC_23 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that cash out amount can be within 6 digits | 546789 | 1. Go to the 'Cashout' module 2. Choose or input agent number 3. Input the amount more than 6 digits | The 7th digit should not be taken | Successful | Passed | Passed | High
TC_24 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that 'Agent' field shows only saved or recently transactioned agents' list |  | 1. Go to the 'Cashout' module 2. Choose 'Agent' field 3. See if the saved agents list is showing | There should appear a list of saved agents numbers below | There is a list | Passed | Passed | High
TC_25 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that the favorite agent number is saved for less cashout charge |  | 1. Go to the 'Cashout' module 2. Click on the 'হাজারে ১৪.৯০ টাকায় ক্যাশআউট করতে চাপুন' 3. Find the saved agent number | The number should be appearing there | Successful | Passed | Passed | High
TC_26 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that more agent numbers can be added |  | 1. Go to the 'Cashout' module 2. Click on the 'হাজারে ১৪.৯০ টাকায় ক্যাশআউট করতে চাপুন' 3. Click on the '+' sign at the bottom right corner | After adding the number, an error message should be popped up that only one agent number can be saved within one month | There comes a message | Passed | Passed | High
TC_27 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that QR code scanner opens to take QR code picture |  | 1. Go to the 'Cashout' module 2. Go to the QR code scan button | This should open the camera for scanning | Successful | Passed | Passed | High
TC_28 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that number or name field is labelled properly |  | 1. Go to the 'Cashout' module 2. Check whether the number or name field is labelled | This should show the labelling always | Successful | Passed | Passed | High
TC_29 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that 'ATM' field shows only instructions and list of partner banks |  | 1. Go to the 'Cashout' module 2. Go to the ATM tab 3. See the instructions tabs | There should be two seperate buttons with instructions | There are seperate buttons containing instructions | Passed | Passed | High
TC_30 | Paybill | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that only accurate format of Credit card number allows to go further |  | 1. Go to the 'Pay bill' module 2. Choose Credit card from the list 3. Choose the bank 4. Give any number in the Card number | Entering wrong format of number should not appear the Next button | Successful | Passed | Passed | High
TC_31 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that entering on each type of bill opens up all the institutions of that bill paying |  | 1. Go to the 'Pay bill' module 2. Choose the company name from the list 3. See the list below | There should appear the whole list of institutions/companies | There is a whole list of linked companies | Passed | Passed | High
TC_32 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that any bill paid through Bkash is recorded in the 'Pay bill details' section |  | 1. Go to the 'Pay bill' module 2. Go to the 'Pay bill details' | Any bill paid through Bkash should be recorded in the 'Pay bill details' section | There is no bill paid through Bkash so there is no record added | Passed | Passed | High
TC_33 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that in case of Electricity bill; after inputting the identification number, bill amount is not displayed |  | 1. Go to the 'Pay bill' module 2. Choose the company name from the list 3. Choose the bill type 4. Input the account number and contact number 5. Input the bill amount | There should not show any amount but should input the amount manually | Successful | Passed | Passed | High
TC_34 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that in case of water bill; the timeline is selectable for paying the bill of any specific month |  | 1. Go to the 'Pay bill' module 2. Choose the company name from the list 3. Choose the bill type 4. Select the timeline from dropdown | There should be a dropdown available in order to select timeline | A dropdown containing month and year is available | Passed | Passed | High
TC_35 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that in case of water bill; entering more than 25 digits for bill number does not allow to go further |  | 1. Go to the 'Pay bill' module 2. Choose the company name from the list 3. Choose the bill type 4. Input more than 25 digits for the bill number | This should not appear the next button | Successful | Passed | Passed | High
TC_36 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that bill receipts are accurately recorded in the 'Receipt and Token' section |  | 1. Go to the 'Pay bill' module 2. Go to the 'Receipt and Token' section 3. Check Bill receipt | All the paid bill receipts should be recorded in the 'Bill receipt' section | Bill receipts are there | Passed | Passed | High
TC_37 | Send money | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that the usable balance is showing accurate |  | 1. Go to the 'Send Money' module 2. Select the number 3. Go to the next page where usable balance is displayed | There should be displayed the accurate usable balance | Successful | Passed | Passed | High
TC_38 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that the favorite number is available for sending money free of cost |  | 1. Go to the 'Send Money' module 2. Check the star marked numbers in the list | The favorite number should be saved and marked as star | The favorite number is showing a star marks at the corner | Passed | Passed | High
TC_39 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that the 'Áuto pay' option is selectable |  | 1. Go to the 'Send Money' module 2. Click on the 'Auto pay' | Áuto pay' should be a seperate option | This option is a seperate field | Passed | Passed | High
TC_40 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that an example video is available to show how to perform auto pay option |  | 1. Go to the 'Send Money' module 2. Click on the 'Auto pay' 3. Click on the video manual | There should be a video available to show steps of enabling auto pay | The video is containing all the steps | Passed | Passed | High
TC_41 | Mobile Recharge | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that, the Mobile Recharge button working |  | 1. Go to the 'Mobile recharge' 2. See whether it is moving to the next page | This should lead to the next page | Successful | Passed | Passed | High
TC_42 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that the 'Name or Number' field is taking only 11 digits | 1782890358 | 1. Go to the 'Mobile recharge' 2. Try to write down more than 11 digits | This should disable the Next button | Successful | Passed | Passed | High
TC_43 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that important notes are available for every offer | 17828903587 | 1. Go to the 'Mobile recharge' 2. Select number 3. See My offer, minutes etc tabs to see important notes | This should display in every tab except Amount | An 'i' icon is there that contains the notes | Passed | Passed | High
TC_44 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that the 'Name or Number' field shows all the list of saved numbers |  | 1. Go to the 'Mobile recharge' 2. See the list appearing below | This should show the list of saved numbers | Successful | Passed | Passed | High
TC_45 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that after entering or selecting number the next page shows all the offers |  | 1. Go to the 'Mobile recharge' 2. Select the number 3. See the next page with different tabs | There should appear different offers like Internet, My offer, Minutes etc | Different tabs have different offering fields | Passed | Passed | High
TC_46 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that the usable balance is showing accurately |  | 1. Go to the 'Mobile recharge' 2. Select the number 3. See the usable balance below in the next page | This should display the amount of usable balance | Successful | Passed | Passed | High
TC_47 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that every tab different available offers |  | 1. Go to the 'Mobile recharge' 2. Select the number 3. See the next page with different tabs | There should appear different offers like Internet, My offer, Minutes, Call rate, Bundle | Successful | Passed | Passed | High
TC_48 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that any offer is selectable regardless of necessary balance |  | 1. Go to the 'Mobile recharge' 2. Select the number 3. See the next page with different tabs 4. Select any offer | This should lead to the next page | The next page opens | Passed | Passed | High
TC_49 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that an "Auto recharge" option is available |  | 1. Go to the 'Mobile recharge' 2. Select the number 3. See the next page with different tabs 4. From the 'Amount' tab, see the 'Auto recharge' option | Auto recharge with settings' option should appear | Successful | Passed | Passed | High
TC_50 |  | 1. The user is already registered 2. The user has logged in 3. The navigation page has appeared | Verify that selecting any offer with greater amount than usable balance shows an error message before inputting pins |  | 1. Go to the 'Mobile recharge' 2. Select the number 3. Select an offer that needs more amount than the usable balance 4. Go to next 5. Input the pin 6. See the message next | This should occur an error message | An error message is coming | Passed | Passed | High